## Start Here
CYBERDYNE SYSTEMS ¦ RISK REGISTER
Project #2 · GRC portfolio simulation · October 2026
Prepared by | Aditi Rajendra Katare
Company | Fictional 50-employee SaaS startup
Purpose | Identify, score, treat, and review cybersecurity and business risks.
Important | All control actions are proposed. No live controls were independently verified.
Residual score warning | Target residual scores are planning placeholders, not measured outcomes.
Known gap | Backup/recovery coverage, immutability, and restore testing are unverified.
Sheets | Risk Register; Scoring Method; Treatment Plan; Framework Mapping.
Frameworks | NIST CSF 2.0; CIS Controls v8.1; selected SOC 2 Trust Services Criteria.
Use limitation | Not an audit, certification, legal opinion, or real-world risk assessment.

## Risk Register
Risk ID | Asset / Process | Asset description | Threat event | Vulnerability / scenario | Likelihood (1-5) | Impact (1-5) | Inherent score | Inherent rating | Recommended treatment | Proposed controls / actions | Accountable owner (role) | Target due date | Control status | Target residual likelihood | Target residual impact | Target residual score | Target residual rating | Framework mapping | Business impact | Risk acceptance / notes
R-01 | Customer database | Customer PII and account records | Unauthorized access / data exfiltration | Over-permissive database roles, weak access reviews, or exposed credentials | 4 | 5 | 20 | Critical | Mitigate | Enforce least-privilege DB roles; private networking; MFA for administrative paths; secrets manager; audit logging; quarterly access review | Platform Engineering Lead | 30 days | Proposed | 3 | 4 | 12 | High | NIST PR.AA, PR.DS, DE.CM; CIS 3, 5, 6, 8; SOC 2 CC6.1, CC6.6, CC7.2 | Customer confidentiality breach, notification costs, regulatory exposure, reputational damage | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-02 | AWS production account | Compute, storage, networking, IAM and production services | Cloud account compromise | Over-privileged IAM, long-lived keys, weak root-account protections | 4 | 5 | 20 | Critical | Mitigate | Require MFA for privileged access; federated identity; prohibit routine root use; short-lived credentials; SCP/permission boundaries where applicable; CloudTrail and alerting | Cloud Security Owner | 30 days | Proposed | 3 | 4 | 12 | High | NIST PR.AA, PR.PS, DE.CM; CIS 5, 6, 8; SOC 2 CC6.1, CC6.6, CC7.2 | Production compromise, data loss, service outage, unexpected cloud spend | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-03 | AWS object storage | Customer uploads, exports, backups | Public exposure of sensitive objects | Misconfigured bucket policies, public access settings, or inadequate review | 3 | 5 | 15 | High | Mitigate | Block public access at account and bucket levels; policy-as-code checks; encryption; access logging; alert on policy changes; periodic exposure scans | Platform Engineering Lead | 21 days | Proposed | 2 | 4 | 8 | Medium | NIST PR.DS, PR.PS, DE.CM; CIS 3, 4, 8; SOC 2 CC6.1, CC6.7, CC7.2 | Bulk data exposure and loss of customer trust | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-04 | GitHub repositories | Source code, workflows, infrastructure definitions | Source-code theft or malicious code injection | Weak branch protections, excessive repository permissions, leaked tokens | 4 | 4 | 16 | High | Mitigate | Protect default branches; require reviews and status checks; enable secret scanning and push protection where available; least-privilege tokens; dependency and code scanning | Engineering Manager | 30 days | Proposed | 3 | 3 | 9 | Medium | NIST PR.PS, PR.AA, DE.CM; CIS 4, 5, 6, 16; SOC 2 CC6.1, CC7.1, CC8.1 | IP loss, supply-chain compromise, production backdoor | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-05 | CI/CD pipelines | Build artifacts, deployment credentials, release process | Pipeline compromise / unauthorized release | Untrusted workflow triggers, over-scoped runners or deployment secrets | 3 | 5 | 15 | High | Mitigate | Pin third-party actions; isolate runners; restrict deployment environments; use OIDC short-lived cloud credentials; require approvals for production; log releases | DevSecOps Lead | 45 days | Proposed | 2 | 4 | 8 | Medium | NIST PR.PS, PR.AA, DE.CM; CIS 4, 5, 16; SOC 2 CC6.1, CC7.1, CC8.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-06 | Employee laptops | Local files, browser sessions, credentials | Malware or ransomware infection | Unmanaged endpoints, delayed patching, weak local admin controls | 4 | 4 | 16 | High | Mitigate | Endpoint protection; full-disk encryption; automatic patching; screen lock; remove local admin by default; device inventory; tested recovery procedures | IT Operations Lead | 30 days | Proposed | 3 | 3 | 9 | Medium | NIST PR.PS, PR.DS, DE.CM, RS.MA; CIS 1, 4, 7, 10; SOC 2 CC6.8, CC7.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-07 | Google Workspace | Email, files, calendars and identity | Business email compromise / phishing | Insufficient phishing-resistant MFA, weak email protections, poor reporting habits | 4 | 4 | 16 | High | Mitigate | Enforce MFA; disable legacy authentication; configure SPF/DKIM/DMARC; anti-phishing protections; user reporting path; admin audit alerts; recovery hardening | IT Operations Lead | 30 days | Proposed | 3 | 3 | 9 | Medium | NIST PR.AA, PR.AT, DE.CM; CIS 5, 6, 9, 14; SOC 2 CC6.1, CC6.8, CC7.2 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-08 | Slack workspace | Internal discussions, customer context, incident coordination | Sensitive information disclosed to unauthorized users | Loose guest access, broad channel membership, unmanaged app integrations | 3 | 3 | 9 | Medium | Mitigate | Restrict guest access; approve integrations; review workspace admins; define data-sharing rules; offboard promptly; retention and export settings reviewed | IT Operations Lead | 45 days | Proposed | 2 | 2 | 4 | Low | NIST PR.AA, PR.DS, PR.AT; CIS 3, 5, 6, 14; SOC 2 CC6.1, CC6.6 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-09 | Identity and access lifecycle | Employee, contractor and administrator identities | Orphaned accounts retain access after departure | Manual or inconsistent joiner-mover-leaver process | 3 | 5 | 15 | High | Mitigate | Centralized identity inventory; HR-triggered offboarding checklist; revoke sessions and tokens; disable accounts same day; quarterly access recertification with evidence | People Operations + IT | 21 days | Proposed | 2 | 4 | 8 | Medium | NIST PR.AA; CIS 5, 6; SOC 2 CC6.2, CC6.3 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-10 | Secrets and API keys | Application secrets, API tokens, signing keys | Credential theft and unauthorized API use | Secrets committed to repositories, shared in chat, or not rotated | 4 | 4 | 16 | High | Mitigate | Use managed secrets storage; secret scanning; short-lived tokens; documented rotation and revocation; prohibit secrets in tickets/chat; alert on anomalous use | DevSecOps Lead | 30 days | Proposed | 3 | 3 | 9 | Medium | NIST PR.AA, PR.DS, DE.CM; CIS 3, 5, 16; SOC 2 CC6.1, CC6.6, CC7.2 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-11 | Backups and recovery | Customer data, configuration, application state | Irrecoverable data loss or prolonged outage | Backup coverage, immutability, retention, and restore testing not verified | 3 | 5 | 15 | High | Mitigate | Define RPO/RTO; automate encrypted backups; separate backup credentials/account; immutable copies where feasible; monthly restore tests; document evidence and recovery runbooks | Platform Engineering Lead | 30 days | Proposed; known validation gap | 2 | 4 | 8 | Medium | NIST PR.DS, RC.RP, RC.CO; CIS 11; SOC 2 A1.2, A1.3, CC7.5 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-12 | Production availability | Customer-facing SaaS service | DDoS, cloud outage, or capacity failure | Single points of failure, limited resilience testing, unclear escalation | 3 | 4 | 12 | High | Mitigate | Set service objectives; configure managed DDoS protection; capacity alerts; multi-AZ where justified; incident runbook; test failover and customer communications | SRE / Platform Lead | 60 days | Proposed | 2 | 3 | 6 | Medium | NIST PR.IR, DE.AE, RS.MA, RC.RP; CIS 11, 12, 13; SOC 2 A1.1, A1.2, CC7.4 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-13 | Third-party SaaS vendors | Customer and company data held by vendors | Vendor breach or service dependency failure | No formal vendor inventory, due diligence, or periodic reassessment | 3 | 4 | 12 | High | Mitigate | Maintain vendor register; tier by data/access/criticality; review security reports and DPAs; document subprocessors; define exit and outage plans; annual reassessment | GRC / Procurement Owner | 60 days | Proposed | 2 | 3 | 6 | Medium | NIST GV.SC, ID.RA; CIS 15; SOC 2 CC3.2, CC9.2 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-14 | Customer privacy and data handling | Personal data across product, support and analytics | Privacy incident or non-compliant processing | Data inventory, retention rules, deletion workflow, and access boundaries may be incomplete | 3 | 5 | 15 | High | Mitigate | Map data flows; document purpose and retention; minimize collection; implement deletion requests; restrict production data in non-production; review applicable legal obligations | Privacy Owner + Product Lead | 60 days | Proposed | 2 | 4 | 8 | Medium | NIST GV.PO, PR.DS, ID.AM; CIS 3; SOC 2 CC6.1, CC6.5, CC6.7 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-15 | Security logging and monitoring | Cloud, identity, endpoints, applications | Threat activity goes undetected | Log sources, retention, alert ownership and response SLAs not confirmed | 4 | 4 | 16 | High | Mitigate | Inventory critical logs; centralize and protect them; define retention; alert on privileged changes and suspicious authentication; assign on-call ownership; test detections quarterly | Security Lead | 45 days | Proposed | 3 | 3 | 9 | Medium | NIST DE.CM, DE.AE, RS.MA; CIS 8, 13, 17; SOC 2 CC7.2, CC7.3 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-16 | Incident response capability | People, runbooks, evidence, communications | Slow or inconsistent response to security incident | No evidence of a tested incident response exercise | 3 | 4 | 12 | High | Mitigate | Approve incident response plan; define severity and escalation; preserve evidence; prepare customer/legal communications; conduct tabletop exercise twice yearly and track actions | Security Lead | 45 days | Proposed | 2 | 3 | 6 | Medium | NIST RS.MA, RS.AN, RS.CO, RS.MI; CIS 17; SOC 2 CC7.3, CC7.4 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-17 | Vulnerability and patch management | Servers, containers, dependencies, endpoints | Known vulnerability exploited before remediation | No verified asset-linked remediation SLAs or exception process | 4 | 4 | 16 | High | Mitigate | Run authenticated scans where appropriate; scan dependencies and images; prioritize by exploitability and exposure; set severity-based SLAs; track exceptions and retest fixes | Engineering Manager | 30 days | Proposed | 3 | 3 | 9 | Medium | NIST ID.RA, PR.PS, DE.CM; CIS 7, 16; SOC 2 CC7.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-18 | Software supply chain | Open-source packages, container images, build dependencies | Compromised or vulnerable dependency enters production | Unpinned dependencies, weak review of packages, limited provenance controls | 3 | 4 | 12 | High | Mitigate | Generate SBOM for releases; automate dependency alerts; pin and verify dependencies; review critical maintainers; sign artifacts where practical; define emergency upgrade process | DevSecOps Lead | 60 days | Proposed | 2 | 3 | 6 | Medium | NIST PR.PS, ID.RA; CIS 2, 16; SOC 2 CC7.1, CC8.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-19 | Financial operations and cloud spend | Cloud billing, subscriptions, payment workflows | Cloud cost spike or fraudulent payment change | Weak budget alerts, limited separation of duties, vendor-payment change verification unclear | 3 | 3 | 9 | Medium | Mitigate | Set budgets and anomaly alerts; require independent approval for payment-detail changes; restrict billing admins; monthly cost review; maintain documented vendor payment verification | Finance Lead + Cloud Owner | 45 days | Proposed | 2 | 2 | 4 | Low | NIST GV.OV, PR.AA; CIS 5, 6; SOC 2 CC5.2, CC6.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-20 | Business continuity and key-person dependency | Critical product operations and support | Critical function stalls when key staff unavailable | Runbooks, cross-training, and succession coverage not validated | 3 | 4 | 12 | High | Mitigate | Identify critical roles; document runbooks; cross-train backups; maintain emergency contacts; test continuity scenarios and review coverage quarterly | COO / Engineering Manager | 60 days | Proposed | 2 | 3 | 6 | Medium | NIST GV.RR, RC.RP, RC.CO; CIS 17; SOC 2 CC2.2, A1.2 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-21 | Customer support tooling | Support tickets, attachments, impersonation workflows | Social engineering leads to account takeover or data disclosure | Support identity verification and privileged actions may lack dual control | 3 | 4 | 12 | High | Mitigate | Create identity-verification playbook; restrict support impersonation; log and review sensitive actions; require step-up approval for high-risk account changes | Customer Support Lead | 45 days | Proposed | 2 | 3 | 6 | Medium | NIST PR.AA, PR.AT, DE.CM; CIS 5, 6, 14; SOC 2 CC6.1, CC6.6 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-22 | Product authorization logic | Tenant data, API endpoints, admin functions | Cross-tenant data exposure or privilege escalation | Authorization tests may not cover tenant boundaries and object-level access | 3 | 5 | 15 | High | Mitigate | Threat-model tenant boundaries; add object-level authorization tests; perform code review and independent security testing; log denied/suspicious access; add regression tests | Product Security / Engineering Lead | 45 days | Proposed | 2 | 4 | 8 | Medium | NIST PR.PS, ID.RA, DE.CM; CIS 16; SOC 2 CC6.1, CC7.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-23 | Security awareness and reporting | Employees and contractors | Human error enables phishing, data leakage or fraud | Training cadence, role-based training and reporting metrics not verified | 4 | 3 | 12 | High | Mitigate | Run onboarding and annual awareness training; role-based secure coding/admin training; simple phishing-reporting channel; track completion and incident lessons | People Operations + Security Lead | 60 days | Proposed | 3 | 2 | 6 | Medium | NIST PR.AT; CIS 14; SOC 2 CC2.2, CC3.2 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.
R-24 | Risk governance and compliance evidence | Risk register, policies, control evidence, customer assurance | Audit or customer assurance failure due to unsupported control claims | No verified control owners, evidence cadence, or formal risk acceptance record | 3 | 4 | 12 | High | Mitigate | Assign control owners; maintain evidence index; document risk acceptance authority; quarterly risk review; map controls to applicable commitments; record exceptions and approvals | GRC Owner | 30 days | Proposed | 2 | 3 | 6 | Medium | NIST GV.OV, GV.PO, GV.RR; CIS 17; SOC 2 CC1.2, CC3.2, CC4.1 | Operational disruption, financial loss, or reduced customer trust. | Target residual is an estimate for planning only. Re-score after controls are implemented and evidence is tested.

## Scoring Method
Field | Definition / rule
Assessment horizon | Assumed next 12 months; validate for real use.
Likelihood | 1 Rare; 2 Unlikely; 3 Possible; 4 Likely; 5 Almost Certain.
Impact | 1 Insignificant; 2 Minor; 3 Moderate; 4 Major; 5 Severe.
Inherent risk | Likelihood × Impact before proposed mitigation.
Low | 1–4: routine management and review.
Medium | 5–9: assign owner and track treatment.
High | 10–16: prioritize treatment; monthly review.
Critical | 17–25: prompt escalation and interim safeguards.
Target residual risk | Planning estimate only. Re-score after implementation and evidence-based testing.
Initial target assumption | Draft placeholder reduces likelihood and impact each by one level, minimum 1. Not measured.
Control status | Proposed means not verified. Policies do not prove deployment or effectiveness.

## Treatment Plan
Risk ID | Asset / Process | Inherent score | Inherent rating | Treatment | Proposed action | Owner | Target due date | Control status | Target residual score | Target residual rating
R-01 | Customer database | 20 | Critical | Mitigate | Enforce least-privilege DB roles; private networking; MFA for administrative paths; secrets manager; audit logging; quarterly access review | Platform Engineering Lead | 30 days | Proposed | 12 | High
R-02 | AWS production account | 20 | Critical | Mitigate | Require MFA for privileged access; federated identity; prohibit routine root use; short-lived credentials; SCP/permission boundaries where applicable; CloudTrail and alerting | Cloud Security Owner | 30 days | Proposed | 12 | High
R-03 | AWS object storage | 15 | High | Mitigate | Block public access at account and bucket levels; policy-as-code checks; encryption; access logging; alert on policy changes; periodic exposure scans | Platform Engineering Lead | 21 days | Proposed | 8 | Medium
R-04 | GitHub repositories | 16 | High | Mitigate | Protect default branches; require reviews and status checks; enable secret scanning and push protection where available; least-privilege tokens; dependency and code scanning | Engineering Manager | 30 days | Proposed | 9 | Medium
R-05 | CI/CD pipelines | 15 | High | Mitigate | Pin third-party actions; isolate runners; restrict deployment environments; use OIDC short-lived cloud credentials; require approvals for production; log releases | DevSecOps Lead | 45 days | Proposed | 8 | Medium
R-06 | Employee laptops | 16 | High | Mitigate | Endpoint protection; full-disk encryption; automatic patching; screen lock; remove local admin by default; device inventory; tested recovery procedures | IT Operations Lead | 30 days | Proposed | 9 | Medium
R-07 | Google Workspace | 16 | High | Mitigate | Enforce MFA; disable legacy authentication; configure SPF/DKIM/DMARC; anti-phishing protections; user reporting path; admin audit alerts; recovery hardening | IT Operations Lead | 30 days | Proposed | 9 | Medium
R-08 | Slack workspace | 9 | Medium | Mitigate | Restrict guest access; approve integrations; review workspace admins; define data-sharing rules; offboard promptly; retention and export settings reviewed | IT Operations Lead | 45 days | Proposed | 4 | Low
R-09 | Identity and access lifecycle | 15 | High | Mitigate | Centralized identity inventory; HR-triggered offboarding checklist; revoke sessions and tokens; disable accounts same day; quarterly access recertification with evidence | People Operations + IT | 21 days | Proposed | 8 | Medium
R-10 | Secrets and API keys | 16 | High | Mitigate | Use managed secrets storage; secret scanning; short-lived tokens; documented rotation and revocation; prohibit secrets in tickets/chat; alert on anomalous use | DevSecOps Lead | 30 days | Proposed | 9 | Medium
R-11 | Backups and recovery | 15 | High | Mitigate | Define RPO/RTO; automate encrypted backups; separate backup credentials/account; immutable copies where feasible; monthly restore tests; document evidence and recovery runbooks | Platform Engineering Lead | 30 days | Proposed; known validation gap | 8 | Medium
R-12 | Production availability | 12 | High | Mitigate | Set service objectives; configure managed DDoS protection; capacity alerts; multi-AZ where justified; incident runbook; test failover and customer communications | SRE / Platform Lead | 60 days | Proposed | 6 | Medium
R-13 | Third-party SaaS vendors | 12 | High | Mitigate | Maintain vendor register; tier by data/access/criticality; review security reports and DPAs; document subprocessors; define exit and outage plans; annual reassessment | GRC / Procurement Owner | 60 days | Proposed | 6 | Medium
R-14 | Customer privacy and data handling | 15 | High | Mitigate | Map data flows; document purpose and retention; minimize collection; implement deletion requests; restrict production data in non-production; review applicable legal obligations | Privacy Owner + Product Lead | 60 days | Proposed | 8 | Medium
R-15 | Security logging and monitoring | 16 | High | Mitigate | Inventory critical logs; centralize and protect them; define retention; alert on privileged changes and suspicious authentication; assign on-call ownership; test detections quarterly | Security Lead | 45 days | Proposed | 9 | Medium
R-16 | Incident response capability | 12 | High | Mitigate | Approve incident response plan; define severity and escalation; preserve evidence; prepare customer/legal communications; conduct tabletop exercise twice yearly and track actions | Security Lead | 45 days | Proposed | 6 | Medium
R-17 | Vulnerability and patch management | 16 | High | Mitigate | Run authenticated scans where appropriate; scan dependencies and images; prioritize by exploitability and exposure; set severity-based SLAs; track exceptions and retest fixes | Engineering Manager | 30 days | Proposed | 9 | Medium
R-18 | Software supply chain | 12 | High | Mitigate | Generate SBOM for releases; automate dependency alerts; pin and verify dependencies; review critical maintainers; sign artifacts where practical; define emergency upgrade process | DevSecOps Lead | 60 days | Proposed | 6 | Medium
R-19 | Financial operations and cloud spend | 9 | Medium | Mitigate | Set budgets and anomaly alerts; require independent approval for payment-detail changes; restrict billing admins; monthly cost review; maintain documented vendor payment verification | Finance Lead + Cloud Owner | 45 days | Proposed | 4 | Low
R-20 | Business continuity and key-person dependency | 12 | High | Mitigate | Identify critical roles; document runbooks; cross-train backups; maintain emergency contacts; test continuity scenarios and review coverage quarterly | COO / Engineering Manager | 60 days | Proposed | 6 | Medium
R-21 | Customer support tooling | 12 | High | Mitigate | Create identity-verification playbook; restrict support impersonation; log and review sensitive actions; require step-up approval for high-risk account changes | Customer Support Lead | 45 days | Proposed | 6 | Medium
R-22 | Product authorization logic | 15 | High | Mitigate | Threat-model tenant boundaries; add object-level authorization tests; perform code review and independent security testing; log denied/suspicious access; add regression tests | Product Security / Engineering Lead | 45 days | Proposed | 8 | Medium
R-23 | Security awareness and reporting | 12 | High | Mitigate | Run onboarding and annual awareness training; role-based secure coding/admin training; simple phishing-reporting channel; track completion and incident lessons | People Operations + Security Lead | 60 days | Proposed | 6 | Medium
R-24 | Risk governance and compliance evidence | 12 | High | Mitigate | Assign control owners; maintain evidence index; document risk acceptance authority; quarterly risk review; map controls to applicable commitments; record exceptions and approvals | GRC Owner | 30 days | Proposed | 6 | Medium

## Framework Mapping
Risk ID | Risk / process | Indicative mapping | Mapping caveat
R-01 | Customer database | NIST PR.AA, PR.DS, DE.CM; CIS 3, 5, 6, 8; SOC 2 CC6.1, CC6.6, CC7.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-02 | AWS production account | NIST PR.AA, PR.PS, DE.CM; CIS 5, 6, 8; SOC 2 CC6.1, CC6.6, CC7.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-03 | AWS object storage | NIST PR.DS, PR.PS, DE.CM; CIS 3, 4, 8; SOC 2 CC6.1, CC6.7, CC7.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-04 | GitHub repositories | NIST PR.PS, PR.AA, DE.CM; CIS 4, 5, 6, 16; SOC 2 CC6.1, CC7.1, CC8.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-05 | CI/CD pipelines | NIST PR.PS, PR.AA, DE.CM; CIS 4, 5, 16; SOC 2 CC6.1, CC7.1, CC8.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-06 | Employee laptops | NIST PR.PS, PR.DS, DE.CM, RS.MA; CIS 1, 4, 7, 10; SOC 2 CC6.8, CC7.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-07 | Google Workspace | NIST PR.AA, PR.AT, DE.CM; CIS 5, 6, 9, 14; SOC 2 CC6.1, CC6.8, CC7.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-08 | Slack workspace | NIST PR.AA, PR.DS, PR.AT; CIS 3, 5, 6, 14; SOC 2 CC6.1, CC6.6 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-09 | Identity and access lifecycle | NIST PR.AA; CIS 5, 6; SOC 2 CC6.2, CC6.3 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-10 | Secrets and API keys | NIST PR.AA, PR.DS, DE.CM; CIS 3, 5, 16; SOC 2 CC6.1, CC6.6, CC7.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-11 | Backups and recovery | NIST PR.DS, RC.RP, RC.CO; CIS 11; SOC 2 A1.2, A1.3, CC7.5 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-12 | Production availability | NIST PR.IR, DE.AE, RS.MA, RC.RP; CIS 11, 12, 13; SOC 2 A1.1, A1.2, CC7.4 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-13 | Third-party SaaS vendors | NIST GV.SC, ID.RA; CIS 15; SOC 2 CC3.2, CC9.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-14 | Customer privacy and data handling | NIST GV.PO, PR.DS, ID.AM; CIS 3; SOC 2 CC6.1, CC6.5, CC6.7 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-15 | Security logging and monitoring | NIST DE.CM, DE.AE, RS.MA; CIS 8, 13, 17; SOC 2 CC7.2, CC7.3 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-16 | Incident response capability | NIST RS.MA, RS.AN, RS.CO, RS.MI; CIS 17; SOC 2 CC7.3, CC7.4 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-17 | Vulnerability and patch management | NIST ID.RA, PR.PS, DE.CM; CIS 7, 16; SOC 2 CC7.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-18 | Software supply chain | NIST PR.PS, ID.RA; CIS 2, 16; SOC 2 CC7.1, CC8.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-19 | Financial operations and cloud spend | NIST GV.OV, PR.AA; CIS 5, 6; SOC 2 CC5.2, CC6.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-20 | Business continuity and key-person dependency | NIST GV.RR, RC.RP, RC.CO; CIS 17; SOC 2 CC2.2, A1.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-21 | Customer support tooling | NIST PR.AA, PR.AT, DE.CM; CIS 5, 6, 14; SOC 2 CC6.1, CC6.6 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-22 | Product authorization logic | NIST PR.PS, ID.RA, DE.CM; CIS 16; SOC 2 CC6.1, CC7.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-23 | Security awareness and reporting | NIST PR.AT; CIS 14; SOC 2 CC2.2, CC3.2 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.
R-24 | Risk governance and compliance evidence | NIST GV.OV, GV.PO, GV.RR; CIS 17; SOC 2 CC1.2, CC3.2, CC4.1 | High-level cross-reference only. Validate version, scope, criteria, and evidence; does not assert compliance.